## VM setup
Setting HA envirnoment using 5VM
Sr.No | Activity | Task to be perform | Commands | Ubuntu 20.04 dependency
VM verification
1 | VM allocation | Amyris team
2 | VM connectivity verification | Shreeyansh team | ssh ssawant@prod114 ssh ssawant@prod115 ssh ssawant@prod116 ssh ssawant@prod117 ssh ssawant@prod119
3 | Verification of sudo access | Shreeyansh team | sudo su - ssawant
4 | Verification of allocated IP'S | Shreeyansh team | prod114: 10.10.18.81 prod115: 10.10.18.84 prod116: 10.10.18.85 prod117: 10.10.18.86 prod119: 10.10.22.44
5 | Mount point verification | Shreeyansh team | df -h /pg_xlog /DATA /ARCHIVE /BACKUP
6 | VM RAM &Processer | Shreeyansh team | free -g: RAM: 15GB lscpu: CPU core:4
PostgreSQL Installation
7 | Postgresql version | Shreeyansh team | Postgresql-12.5
9 | Postgres installation | Shreeyansh team | http://ci.amyris.local/view/pgdb/job/test_postgres_install/ | sudo apt-get -y install readline8 readline-dev
8 | Verification of installation path | Shreeyansh team | /opt/PostgreSQL/12.5/ ls -lrth share include lib bin
Cluster Creation
10 | Cluster creation | Shreeyansh team | http://ci.amyris.local/job/test_postgres_cluster_init/
11 | Data directory verification | Shreeyansh team | cd /DATA/postgres/12.5/amyris
12 | Set bash profile | Shreeyansh team | nano .bash_profile then copy the script and paste into 'bash_profile' then run this query source .bash_profile Bash profile for prod114: #!/bin/bash export PATH=/opt/PostgreSQL/12.5/bin:$PATH export PGHOME=/opt/PostgreSQL/12.5 export PGDATA=/DATA/postgres/12.5/amyris export PGPORT=5432 export PGDATABASE=postgres export PGUSER=postgres export PGARCH=/ARCHIVE export XLOG=/pg_xlog export HOSTNAME=prod114 export PGHOST=/tmp export PS1='postgres@prod114:~$' export LD_LIBRARY_PATH=/opt/PostgreSQL/12.5/lib:$LD_LIBRARY_PATH export USERHOME=/home/postgres Bash profile for prod115: #!/bin/bash export PATH=/opt/PostgreSQL/12.5/bin:$PATH export PGHOME=/opt/PostgreSQL/12.5 export PGDATA=/DATA/postgres/12.5/amyris export PGPORT=5432 export PGDATABASE=postgres export PGUSER=postgres export PGARCH=/ARCHIVE export XLOG=/pg_xlog export HOSTNAME=prod115 export PGHOST=/tmp export PS1='postgres@prod115:~$' export LD_LIBRARY_PATH=/opt/PostgreSQL/12.5/lib:$LD_LIBRARY_PATH export USERHOME=/home/postgres Bash profile for prod116: #!/bin/bash export PATH=/opt/PostgreSQL/12.5/bin:$PATH export PGHOME=/opt/PostgreSQL/12.5 export PGDATA=/DATA/postgres/12.5/amyris export PGPORT=5432 export PGDATABASE=postgres export PGUSER=postgres export PGARCH=/ARCHIVE export XLOG=/pg_xlog export HOSTNAME=prod116 export PGHOST=/tmp export PS1='postgres@prod116:~$' export LD_LIBRARY_PATH=/opt/PostgreSQL/12.5/lib:$LD_LIBRARY_PATH export USERHOME=/home/postgres
13 | postgres instance status | Shreeyansh team | sudo service postgresql-12.5 status
14 | Verification of contrib-modules | Shreeyansh team | psql \c template1\dx citext dblink fuzzystrmatch intarray pg_buffercache pg_stat_statements pg_trgm pgcrypto plpgsql uuid-ossp
Mandatory tools
15 | pgcluu installation | Shreeyansh team | http://ci.amyris.local/view/pgdb/job/postgres%20pgcluu%20install/
16 | Pgbadger installation | Shreeyansh team | http://ci.amyris.local/view/pgdb/job/postgres%20pgbadger%20install/
17 | pg_repack installation | Shreeyansh team | http://ci.amyris.local/view/pgdb/job/pg_repack/ | sudo apt-get install libc6-i386 sudo apt-get install lib32gcc-s1 sudo apt-get install lib32stdc++6 sudo apt-get install libclang-common-9-dev
18 | pgpool installation on prod110 and prod111 VM | Shreeyansh team | http://ci.amyris.local/view/pgdb/job/pgpool_installation/ | sudo apt-get -y install libssl-dev
19 | Installation of postgres client on pgpool VM | Shreeyansh team | sudo apt install postgresql-client-12
20 | Copy all SY_dbascripts to all postgres instances | Shreeyansh team | scp /home/postgres/SY_dbascripts/ postgres@prod114:/home/postgres/SY_dbascripts/
21 | Copy transaction wal to pg_xlog mount ponit | Shreeyansh team | sudo service postgresql-12.5 stop cp -r /DATA/postgres/12.5/amyris/pg_wal/* /pg_xlog mv /DATA/postgres/12.5/amyris/pg_wal/ pg_wal_old ln -s /pg_xlog /DATA/postgres/12.5/amyris/pg_wal cd /DATA/postgres/12.5/amyris/ pg_wal -> /pg_xlog /opt/PostgreSQL/12.5/bin/pg_ctl -D /DATA/postgres/12.5/amyris start
22 | Postgres auto start stop | Shreeyansh team | sudo service postgresql-12.5 status sudo service postgresql-12.5 stop sudo reboot ssh ssawant@prod114 top -u postgres sudo service postgresql-12.5 status df -h top -u postgres sudo service postgresql-12.5 stop sudo service postgresql-12.5 start
16 | systemctl postgresql start | Shreeyansh team | sudo systemctl start postgresql.service
17 | systemctl postgresql stop | Shreeyansh team | sudo systemctl stop postgresql.service
18 | systemctl postgresql status | Shreeyansh team | sudo systemctl status postgresql.service
23 | sshkey-gen betwen all postgres VM and pgpool VM | Shreeyansh team | ssh-keygen between prod114 to prod115: ssh-keygen ssh-copy-id ssawant@prod115 ssh ssawant@prod115 ssh-keygen between prod115 to prod114: ssh-keygen ssh-copy-id ssawant@prod114 ssh ssawant@prod114 ssh-keygen between prod114 to prod116: ssh-keygen ssh-copy-id ssawant@prod116 ssh ssawant@prod116 ssh-keygen between prod116 to prod114: ssh-keygen ssh-copy-id ssawant@prod114 ssh ssawant@prod114 ssh-keygen between prod108 to prod115: ssh-keygen ssh-copy-id ssawant@prod115 ssh ssawant@prod115 ssh-keygen between prod115 to prod108: ssh-keygen ssh-copy-id ssawant@prod108 ssh ssawant@prod108 ssh-keygen between prod108 to prod116: ssh-keygen ssh-copy-id ssawant@prod116 ssh ssawant@prod116 ssh-keygen between prod116 to prod108: ssh-keygen ssh-copy-id ssawant@prod108 ssh ssawant@prod108 ssh-keygen between prod109 to prod115: ssh-keygen ssh-copy-id ssawant@prod115 ssh ssawant@prod115 ssh-keygen between prod115 to prod109: ssh-keygen ssh-copy-id ssawant@prod109 ssh ssawant@prod109 ssh-keygen between prod109 to prod116: ssh-keygen ssh-copy-id postgres@prod116 ssh postgres@prod116 ssh-keygen between prod116 to prod109: ssh-keygen ssh-copy-id postgres@prod109 ssh postgres@prod109
24 | Pgpool auto start stop | Shreeyansh team | Create services to init.d: 1.Create the script to /etc/init.d/pgpoolstart-service - sudo touch /etc/init.d/pgpoolstart-service - sudo chmod 755 /etc/init.d/pgpoolstart-service #!/bin/bash /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf -n -D > /opt/pgpool-4.2.0/pgpool/pgpool.log 2>&1 & 2.Give execution permission: sudo chmod 755 /etc/init.d/pgpoolstart-service 3.cd /etc - sudo nano rc.local #!/bin/sh -e # # rc.local # # This script is executed at the end of each multiuser runlevel. # Make sure that the script will "exit 0" on success or any other # value on error. # # In order to enable or disable this script just change the execution # bits. # # By default this script does nothing. #/opt/pgpool-4.0.4/etc/pgpool_start.sh /etc/init.d/pgpoolstart-service exit 0 4.sudo chmod 755 /etc/rc.local 5.sudo systemctl daemon-reload 6.stop pgpool manually: cd /opt/pgpool-4.2.0/etc/ sudo sh pgpool_stop.sh 7.sudo service pgpoolstart-service 8.stop pgpool manually: cd /opt/pgpool-4.2.0/etc/ sudo sh pgpool_stop.sh 9.Start service at reboot: reboot system using command: sudo reboot 10.check service command working or not ps -ef ¦ grep pgpool
Replication set up
25 | sshkey-gen betwen all postgres users | Shreeyansh team | ssh-keygen between postgres instance prod114,prod115,prod116: ssh-keygen between prod114 to prod115: ssh-keygen ssh-copy-id postgres@prod115 ssh postgres@prod115 ssh-keygen between prod114 to prod116: ssh-keygen ssh-copy-id postgres@prod116 ssh postgres@prod116 ssh-keygen between prod108 to prod116: ssh-keygen ssh-copy-id postgres@prod116 ssh postgres@prod116 ssh-keygen between prod115 to prod114: ssh-keygen ssh-copy-id postgres@prod114 ssh postgres@prod114 ssh-keygen between prod116 to prod114: ssh-keygen ssh-copy-id postgres@prod114 ssh postgres@prod114 ssh-keygen between prod116 to prod115: ssh-keygen ssh-copy-id postgres@prod115 ssh postgres@prod115
26 | Replication setup on prod107, prod108, prod109 VM | Shreeyansh team | Setup as per postgresql-12.5 version
Replication steps
1 | Master server IP: prod114: 10.10.18.81 Slave IP: prod115: 10.10.18.84 DR: prod116: 10.10.18.85 | Shreeyansh team
2 | Master configuration:
| Create a User for replication in the Master: | Shreeyansh team | postgres=# CREATE USER rep WITH REPLICATION ENCRYPTED PASSWORD '75a384057459ae8e69fb9a98a249b4f4'; CREATE ROLE
| Modifying this parameter in postgres.conf file it requires a restart of the PostgreSQL instance to get the change into effect: | Shreeyansh team | cd /DATA/postgres/12.5/amyris nano postgresql.conf listen_addresses='*' wal_level = replica shared_buffers = 4GB checkpoint_timeout = 5min max_wal_size = 1GB min_wal_size = 80MB archive_mode = on archive_command = 'cp -i %p /ARCHIVE/%f && scp %p postgres@prod115:/ARCHIVE/%f && scp %p postgres@prod116:/ARCHIVE/%f' hot_standby = on
| Allow replication connections from Standby to Master by appending a similar line as following to the pg_hba.conf file of the Master: | Shreeyansh team | cd /DATA/postgres/12.5/amyris nano pg_hba.conf host replication rep 10.10.18.84/24 md5 host replication rep 10.10.18.85/24 md5
| edit .pgpass on all postgres servers |  | cd /home/postgres/ nano .pgpass *:5432:replication:rep:75a384057459ae8e69fb9a98a249b4f4 *:5432:postgres:postgres:postgres
3 | Slave configuration: | Shreeyansh team
| clean 'pg_xlog' and 'amyris' directories |  | rm -rf /pg_xlog/* rm -r /DATA/postgres/12.5/amyris
| connect to slave i.e prod115 and take pg_basebackup of master | Shreeyansh team | pg_basebackup -h 10.10.22.63 -U rep -p 5432 -D /DATA/postgres/12.5/amyris -P -R --waldir=/pg_xlog --max-rate=1000M&
| Verfiy postgres.auto.conf | Shreeyansh team | cat $PGDATA/postgresql.auto.conf primary_conninfo = 'user=rep password='75a384057459ae8e69fb9a98a249b4f4' host=10.10.18.81 port=5432 sslmode=prefer sslcompression=0 gssencmode=prefer krbsrvname=postgres target_session_attrs=any'
| Made changes in postgres.conf file of slave server: | Shreeyansh team | cd /DATA/postgres/12.5/amyris nano postgresql.conf archive_mode = on archive_command = 'cp -i %p /ARCHIVE/%f && scp %p postgres@prod114:/ARCHIVE/%f && scp %p postgres@prod116:/ARCHIVE/%f' restore_command = 'cp -i /ARCHIVE/%f %p' hot_standby = on log_directory = '/BACKUP/pg_logs/prod115/'
| Start PostgreSQL using pg_ctl on the Standby. | Shreeyansh team | ssh ssawant@prod115 sudo service postgresql-12.5 start
| Verify the replication between the Master and the Standby: | Shreeyansh team | psql -h localhost -p 5432 select * from pg_stat_replication;
4 | DR configuration | Shreeyansh team
| clean 'pg_xlog' and 'amyris' directories |  | rm -rf /ARCHIVE/* rm -rf /pg_xlog/* rm -r /DATA/postgres/12.5/amyris
| connect to slave i.e prod116 and take pg_basebackup of master | Shreeyansh team | 2
| Verfiy postgres.auto.conf | Shreeyansh team | cat $PGDATA/postgresql.auto.conf primary_conninfo = 'user=rep password='75a384057459ae8e69fb9a98a249b4f4' host=10.10.18.84 port=5432 sslmode=prefer sslcompression=0 gssencmode=prefer krbsrvname=postgres target_session_attrs=any'
| Made changes in postgres.conf file of slave server: | Shreeyansh team | cd /DATA/postgres/12.5/amyris nano postgresql.conf archive_mode = on archive_command = 'cp -i %p /ARCHIVE/%f && scp %p postgres@prod114:/ARCHIVE/%f && scp %p postgres@prod115:/ARCHIVE/%f' restore_command = 'cp -i /ARCHIVE/%f %p' hot_standby = on log_directory = '/BACKUP/pg_logs/prod116/'
| Start PostgreSQL using pg_ctl on the Standby. | Shreeyansh team | ssh ssawant@prod116 sudo service postgresql-12.5 start
| Verify the replication between the Master and the Standby: | Shreeyansh team | psql -h localhost -p 5432 select * from pg_stat_replication;
Postgresql Server Promote Manually
1 | To check system logs while using systemd services | Shreeyansh team | /opt/PostgreSQL/12.5/bin/pg_ctl -D /DATA/postgres/12.5/amyris promote
Systemd postgresql service
1 | Steps to create a systemd postgresql service | Shreeyansh team | ssh ssawant@prod114 1. cd /etc/systemd/system 2. sudo nano postgresql.service 3. Add the below lines [Unit] Description=PostgreSQL database server #After=network.target After=network.target postgresql.service mnt-pg_data.mount [Service] Type=forking User=postgres Group=postgres # Where to send early-startup messages from the server (before the logging # options of postgresql.conf take effect) # This is normally controlled by the global default set by systemd # StandardOutput=syslog # Disable OOM kill on the postmaster OOMScoreAdjust=-1000 # ... but allow it still to be effective for child processes # (note that these settings are ignored by Postgres releases before 9.5) Environment=PG_OOM_ADJUST_FILE=/proc/self/oom_score_adj Environment=PG_OOM_ADJUST_VALUE=0 # Maximum number of seconds pg_ctl will wait for postgres to start. Note that # PGSTARTTIMEOUT should be less than TimeoutSec value. Environment=PGSTARTTIMEOUT=270 Environment=PGDATA=/DATA/postgres/12.5/amyris ExecStart=/opt/PostgreSQL/12.5/bin/pg_ctl -D /DATA/postgres/12.5/amyris start ExecStop=/opt/PostgreSQL/12.5/bin/pg_ctl -D /DATA/postgres/12.5/amyris stop ExecReload=/opt/PostgreSQL/12.5/bin/pg_ctl -D /DATA/postgres/12.5/amyris reload # Give a reasonable amount of time for the server to start up/shut down. # Ideally, the timeout for starting PostgreSQL server should be handled more # nicely by pg_ctl in ExecStart, so keep its timeout smaller than this value. TimeoutSec=300 [Install] WantedBy=multi-user.target 4. sudo systemctl daemon-reload 5. sudo systemctl enable postgresql.service 6. sudo systemctl start postgresql.service
Check System Logs (systemd services)
1 | To check system logs while using systemd services | Shreeyansh team | sudo tail /var/log/syslog
Reset pgwal
1 | command to reset pgwal if needed | Shreeyansh team | ./pg_resetwal -f -D /DATA/postgres/12.5/amyris | use this command very carefully
Archive cleanup command(except current day)
1 | command to use clean archives | Shreeyansh team | find -daystart -mtime +1 -exec rm -f {} \; and find -daystart -mtime 1 -exec rm -f {} \; | use this command very carefully
Mount point open though ess
1 | command to open mountpoint | Shreeyansh team | sudo mkdir -p /BACKUP_$HOSTNAME/ sudo mount essces-hs:/gpfs/amyrisFS1/SQL/Postgres/prod/scan2/pg_backup /BACKUP_$HOSTNAME/ -r
Create symbolic link to generating URL for pgbadger/pgcluu reports
1 | command to create symbolic link | Shreeyansh team | sudo ln -sf /BACKUP/pgbadger_reports /var/www/html/pgbadger_reports | First go to the source directory e.g. cd /BACKUP Then create an link
Apache2 service start/stop (for making URL for pgbadger/pgcluu reports)
1 | command to start apache service | Shreeyansh team | sudo systemctl start apache2.service
2 | command to stop apache service | Shreeyansh team | sudo systemctl stop apache2.service
3 | command to restart apache service | Shreeyansh team | sudo systemctl restart apache2.service
4 | command to check status apache service | Shreeyansh team | sudo systemctl status apache2.service
Postgresql User Creation & Grant Permission Commands
1 | database user creation and grant permission for 'argus_curator' | Shreeyansh team | CREATE USER argus_curator WITH PASSWORD 'argus_curator'; GRANT CONNECT ON DATABASE scan2 TO argus_curator; GRANT USAGE ON SCHEMA argus TO argus_curator; GRANT SELECT,INSERT,UPDATE,DELETE ON ALL TABLES IN SCHEMA argus TO argus_curator; GRANT ALL PRIVILEGES ON ALL SEQUENCES IN SCHEMA argus TO argus_curator; GRANT USAGE ON SCHEMA symmetric_ds TO argus_curator; GRANT SELECT,INSERT,UPDATE,DELETE ON ALL TABLES IN SCHEMA symmetric_ds TO argus_curator; GRANT ALL PRIVILEGES ON ALL SEQUENCES IN SCHEMA symmetric_ds TO argus_curator; GRANT EXECUTE ON ALL FUNCTIONS IN SCHEMA argus TO argus_curator;
Nagios Important commands
1 | NRPE nagios extension serivices restart after any changes at host level | Shreeyansh team | sudo service xinetd restart
2 | Check errors before restart nagios server | Shreeyansh team | sudo /usr/local/nagios/bin/nagios -v /usr/local/nagios/etc/nagios.cfg
3 | Restart the Nagios server | Shreeyansh team | sudo service nagios restart
4 | All nagios services files location | Shreeyansh team | cd /usr/local/nagios/etc/objects
ci job for get sudo access
1 | ci joblink for get sudo access of any server | Shreeyansh team | http://ci.amyris.local/job/postgres_adds_shreeyansh_to_sudo/ | run this ci job with the node which you want for sudo access
Check Directory size
1 | To check actual size of directory | Shreeyansh team | du -sh /BACKUP/
Register port on new VM manually on ubuntu
1 | To register IP with port on new GCP VM | Shreeyansh team | nc -z -v 10.10.18.98 5432
ODBC Drivers install on ubuntu for accessing MS-SQL from terminal
1 | To install ODBC Drivers on ubuntu follow this link and install manually step by step | Shreeyansh team | https://docs.microsoft.com/en-us/sql/connect/odbc/linux-mac/installing-the-microsoft-odbc-driver-for-sql-server?view=sql-server-ver15
2 | Command for access MS-SQL DB from terminal | Shreeyansh team | sqlcmd -S sqlwarehouse1 -d dataout -U dataout_reader -P dataout_reader -W -h -1 -Q "set nocount on select max(id) from hermes_production.dbo.measurement | This is just an example
PostreSQL Active Connections
1 | To check current PostgrSQL active and idle connections | Shreeyansh team | select count(*) from pg_stat_activity where state='active'; -- for active connections select count(*) from pg_stat_activity where state='idle'; -- for idle connections

## Issues
Issues facing on VM building
Sr.no | Issues | Resolution | Remark
1 | Autocomplete issue on postgres user | 1.Made changes in file (sudo nano /etc/passwd) from root user 2.postgres:x:1002:1002::/home/postgres:/bin/sh to postgres:x:1002:1002::/home/postgres:/bin/bash 3.Login with postgres user and verify
2 | Postgres installation script os version upgardation | Verify postgres_install function from git on PGDB branch https://www.google.com/search?channel=fs&client=ubuntu&q=postgres_install%28%29
3 | How to kill stucked sockets | sudo rm /tmp/.s.PGSQL.9999
4 | reset pgwal | ./pg_resetwal -f -D /DATA/postgres/12.5/amyris
5 | ssawant@prod116:/var/log$ sudo systemctl start postgresql.service Failed to start postgresql.service: Transaction order is cyclic. See system logs for details. See system logs and 'systemctl status postgresql.service' for details. | sudo reboot | first of all check 'syslog' sudo tail -f var/log/syslog if got following errors then and only then reboot the server otherwise don't. Jun 7 04:56:17 prod116 systemd[1]: postgresql.service: Found ordering cycle on postgresql@9.6-main.service/start Jun 7 04:56:17 prod116 systemd[1]: postgresql.service: Found dependency on postgresql.service/start Jun 7 04:56:17 prod116 systemd[1]: postgresql.service: Job postgresql@9.6-main.service/start deleted to break ordering cycle starting with postgresql.service/start Jun 7 04:56:17 prod116 systemd[1]: postgresql.service: Found ordering cycle on postgresql@9.6-main.service/start Jun 7 04:56:17 prod116 systemd[1]: postgresql.service: Found dependency on postgresql.service/start Jun 7 04:56:17 prod116 systemd[1]: postgresql.service: Unable to break cycle starting with postgresql.service/start Jun 7 04:56:17 prod116 systemd[1]: Requested transaction contains an unfixable cyclic ordering dependency: Transaction order is cyclic. See system logs for details. Jun 7 04:56:20 prod116 agent[535]: 2021-06-07 04:56:20 PDT ¦ CORE ¦ ERROR ¦ (pkg/collector/python/datadog_agent.go:120 in LogMessage) ¦ postgres:bf624d405e668305 ¦ (postgres.py:450) ¦ Unable to collect postgres metrics.
6 | 2021-06-12 07:05:09: pid 3934597: WARNING: checking setuid bit of if_up_cmd 2021-06-12 07:05:09: pid 3934597: DETAIL: ifup[/usr/sbin/ip] doesn't have setuid bit 2021-06-12 07:05:09: pid 3934597: WARNING: checking setuid bit of if_down_cmd 2021-06-12 07:05:09: pid 3934597: DETAIL: ifdown[/usr/sbin/ip] doesn't have setuid bit 2021-06-12 07:05:09: pid 3934597: WARNING: checking setuid bit of arping command 2021-06-12 07:05:09: pid 3934597: DETAIL: arping[/usr/sbin/arping] doesn't have setuid bit | sudo chmod u+s /usr/sbin/arping sudo chmod u+s /usr/sbin/ip
7 | postgres@prod116:~$ pg_basebackup: error: directory "/pg_xlog" exists but is not empty pg_basebackup: removing data directory "/DATA/postgres/12.5/amyris" | postgres@prod116:~$ rm -rf /pg_xlog/* postgres@prod116:~$ cd /pg_xlog postgres@prod116:~$ ls postgres@prod116:~$ ls -lrtha total 33M drwxr-xr-x 6 root root 4.0K Feb 8 2021 .. -rw------- 1 postgres postgres 16M Oct 23 00:30 .nfs0000000000726ca20000faa7 drwx------ 2 postgres postgres 256K Oct 25 08:28 . postgres@prod116:~$ rm .nfs0000000000726ca20000faa7 | First of all remove all /pg_xlog/* and DATA directory if you still facing same error then check the 'nfs' hidden files in /pg_xlog, and remove then all and then start basebackup

## pgpool_configuration
pgpool configuration steps:
Sr.No | Activity | Task to be perform | Commands
1 | Master pgpool IP: prod117: 10.10.18.86 | Shreeyansh team
2 | create pgpool user on VM | Shreeyansh team | sudo adduser pgpool
3 | Give sudo permission to user pgpool | Shreeyansh team | sudo usermod -a -G sudo pgpool
4 | Verify pgpool installation directory | Shreeyansh team | cd /opt/pgpool-4.2.0/ ls -lt bin etc include lib share
5 | create pgpool directory under /opt/pgpool-4.0.4/ | Shreeyansh team | sudo mkdir /opt/pgpool-4.2.0/pgpool sudo chown -R pgpool:pgpool /opt/pgpool-4.2.0/pgpool/
6 | change permission of installtion directory | Shreeyansh team | sudo chown -R pgpool:pgpool /opt/pgpool-4.2.0/
7 | Set configuration Files | Shreeyansh team | cd /opt/pgpool-4.2.0/etc/ ls -lt cp /opt/pgpool-4.2.0/etc/pcp.conf.sample /opt/pgpool-4.2.0/etc/pcp.conf cp /opt/pgpool-4.2.0/etc/pgpool.conf.sample /opt/pgpool-4.2.0/etc/pgpool.conf cp /opt/pgpool-4.2.0/etc/pool_hba.conf.sample /opt/pgpool-4.2.0/etc/pool_hba.conf
8 | MD5 Password Authentication | Shreeyansh team | cd /opt/pgpool-4.2.0/bin ./pg_md5 -m -f /opt/pgpool-4.2.0/etc/pgpool.conf -u argus_curator -p if required then give entry in pcp.conf otherwise there is no need to do entry in pcp.conf /opt/pgpool-4.2.0/etc$ nano pcp.conf argus_curator:md57ddb4d8898961bfe7e807004a0722e2b same process do for user 'pgpool'
9 | pgpool Connection settings | Shreeyansh team | cd /opt/pgpool-4.2.0/etc$ nano pgpool.conf listen_addresses = '*' port = 9999 Backend Connection Settings: backend_hostname0 = '10.10.18.81' backend_port0 = 5432 backend_weight0 = 1 backend_data_directory0 = '/DATA/postgres/12.5/amyris' backend_flag0 = 'ALLOW_TO_FAILOVER' backend_hostname1 = '10.10.18.84' backend_port1 = 5432 backend_weight1 = 1 backend_data_directory1 = '/DATA/postgres/12.5/amyris' backend_flag1 = 'ALLOW_TO_FAILOVER' backend_hostname2 = '10.10.18.85' backend_port2 = 5432 backend_weight2 = 1 backend_data_directory2 = '/DATA/postgres/12.5/amyris' backend_flag2 = 'ALLOW_TO_FAILOVER' 3) # - Authentication - enable_pool_hba = on pool_passwd = 'pool_passwd' num_init_children = 300 4) # - FILE LOCATIONS pid_file_name = '/opt/pgpool-4.2.0/pgpool/pgpool.pid' logdir = '/opt/pgpool-4.2.0/pgpool' 5) # - Master/Slave Mode master_slave_mode = on master_slave_sub_mode = 'stream' 6) # - HEALTH CHECK health_check_period = 300 health_check_timeout = 300 health_check_user = 'postgres' health_check_password = 'postgres' health_check_database = 'postgres' health_check_max_retries = 0 health_check_retry_delay = 1 connect_timeout = 10000 7) #FAILOVER AND FAILBACK failover_command = '/opt/pgpool-4.2.0/etc/failover.sh %d %h %D %m %H %R %M %P' fail_over_on_backend_error = on search_primary_node_timeout = 300 8) # ONLINE RECOVERY recovery_user = 'nobody' recovery_password = '' recovery_1st_stage_command = '' recovery_2nd_stage_command = '' recovery_timeout = 90 client_idle_limit_in_recovery = 0 09) # WATCHDOG use_watchdog = on trusted_servers = '' ping_path = '/bin' # - Watchdog communication Settings - hostname0 = '10.10.10.86' wd_port0 = 9000 pgpool_port0 = 9999 wd_priority = 1 wd_authkey = '' wd_ipc_socket_dir = '/tmp' hostname1 = '10.10.22.44' wd_port1 = 9000 pgpool_port1 = 9999 11) Lifecheck Setting - wd_monitoring_interfaces_list = 'any' wd_lifecheck_method = 'heartbeat' wd_interval = 10 -- heartbeat mode -- heartbeat_hostname0 = '10.10.18.86' heartbeat_port0 = 9694 heartbeat_device0 = '' heartbeat_hostname1 = '10.10.22.44' heartbeat_port1 = 9694 heartbeat_device1 = '' wd_heartbeat_keepalive = 2 wd_heartbeat_deadtime = 30 12) - Virtual IP control Setting - delegate_IP = '10.10.18.199' # delegate IP address if_cmd_path = '/usr/sbin' if_up_cmd = 'ip addr add $_IP_$/24 dev eth0 label eth0:0' if_down_cmd = 'ip addr del $_IP_$/24 dev eth0 label eth0:0' arping_path = '/usr/sbin' arping_cmd = 'arping -U $_IP_$ -w 1 -I eth0' 13 ) # - Behaivor on escalation Setting - clear_memqcache_on_escalation = on wd_escalation_command = '/opt/pgpool-4.2.0/etc/escalation.sh' wd_de_escalation_command = '/opt/pgpool-4.2.0/etc/de_escalation.sh' and edit the escalation and de_escalation script which is available in /opt/pgpool-4.2.0/etc/'
10 | create pgpool_node_id file | Shreeyansh team | If watchdog feature is enabled, to distingusish which host is which, a 'pgpool_node_id' file is required. You need to create a 'pgpool_node_id' file and specify the pgpool (watchdog) node number (e.g. 0, 1, 2 ...) to identify pgpool (watchdog) host. create 'pgpool_node_id' file at '/opt/pgpool-4.2.0/etc' this location and in this file add your watchdog host id i.e.0,1,2 etc... cd /opt/pgpool-4.2.0/etc touch pgpool_node_id nano pgpool_node_id 0 -> only enter your hostid = i.e.0 or 1 sudo chown -R pgpool:pgpool /opt/pgpool-4.2.0/pgpool_node_id sudo chmod 755 /opt/pgpool-4.2.0/etc/pgpool_node_id
11 | Install 2 utilities | Shreeyansh team | sudo apt-get install net-tools sudo apt install arping
12 | ssh-keygen between pgpool to pgpool ,pgpool to postgres and pgpool(root) to postgres | Shreeyansh team | ssh-keygen between prod117(pgpool) to postgres servers: ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65 ssh-keygen between prod117(pgpool root) to postgres servers: sudo -i ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65 ssh-keygen between prod119(pgpool) to postgres servers: ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65 ssh-keygen between prod119(pgpool root) to postgres servers: sudo -i ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65
13 | pool_hba.conf entries | Shreeyansh team | cd /opt/pgpool-4.2.0/etc nano pool_hba.conf host all all 10.10.18.81/24 md5 host all all 10.10.18.84/24 md5 host all all 10.10.18.85/24 md5 host all all 10.10.18.86/24 md5
14 | pgpool start script | Shreeyansh team | cd /opt/pgpool-4.2.0/etc$ nano pgpool_start.sh #!/bin/bash /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf -n -D > /opt/pgpool-4.2.0/pgpool/pgpool.log 2>&1 &
15 | pgpool stop script | Shreeyansh team | cd /opt/pgpool-4.2.0/etc$ nano pgpool_stop.sh #!/bin/bash /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf -n -D stop > /opt/pgpool-4.2.0/pgpool/pgpool.log 2>&1 &
16 | systemctl start | Shreeyansh team | sudo systemctl start pgpool.service
17 | systemctl stop | Shreeyansh team | sudo systemctl stop pgpool.service
18 | systemctl status | Shreeyansh team | sudo systemctl status pgpool.service
19 | check the connectivity with postgres | Shreeyansh team | psql -p 9999 -U postgres -d postgres -h localhost
20 | Verfied connected nodes | Shreeyansh team | show pool_nodes;
1 | Slave pgpool IP: prod119:10.10.22.44 | Shreeyansh team
2 | create pgpool user on VM | Shreeyansh team | sudo adduser pgpool
3 | Give sudo permission to user pgpool | Shreeyansh team | sudo usermod -a -G sudo pgpool
4 | Verify pgpool installation directory | Shreeyansh team | cd /opt/pgpool-4.2.0/ ls -lt bin etc include lib share
5 | create pgpool directory under /opt/pgpool-4.0.4/ | Shreeyansh team | sudo mkdir /opt/pgpool-4.2.0/pgpool sudo chown -R pgpool:pgpool /opt/pgpool-4.2.0/pgpool/
6 | change permission of installtion directory | Shreeyansh team | sudo chown -R pgpool:pgpool /opt/pgpool-4.2.0/
7 | Set configuration Files | Shreeyansh team | cd /opt/pgpool-4.2.0/etc/ ls -lt cp /opt/pgpool-4.2.0/etc/pcp.conf.sample /opt/pgpool-4.2.0/etc/pcp.conf cp /opt/pgpool-4.2.0/etc/pgpool.conf.sample /opt/pgpool-4.2.0/etc/pgpool.conf cp /opt/pgpool-4.2.0/etc/pool_hba.conf.sample /opt/pgpool-4.2.0/etc/pool_hba.conf
8 | MD5 Password Authentication | Shreeyansh team | cd /opt/pgpool-4.2.0/bin ./pg_md5 -m -f /opt/pgpool-4.2.0/etc/pgpool.conf -u argus_curator -p if required then give entry in pcp.conf otherwise there is no need to do entry in pcp.conf /opt/pgpool-4.2.0/etc$ nano pcp.conf argus_curator:md57ddb4d8898961bfe7e807004a0722e2b same process do for user 'pgpool'
9 | pgpool Connection settings | Shreeyansh team | cd /opt/pgpool-4.2.0/etc$ nano pgpool.conf listen_addresses = '*' port = 9999 Backend Connection Settings: backend_hostname0 = '10.10.18.81' backend_port0 = 5432 backend_weight0 = 1 backend_data_directory0 = '/DATA/postgres/12.5/amyris' backend_flag0 = 'ALLOW_TO_FAILOVER' backend_hostname1 = '10.10.18.84' backend_port1 = 5432 backend_weight1 = 1 backend_data_directory1 = '/DATA/postgres/12.5/amyris' backend_flag1 = 'ALLOW_TO_FAILOVER' backend_hostname2 = '10.10.18.85' backend_port2 = 5432 backend_weight2 = 1 backend_data_directory2 = '/DATA/postgres/12.5/amyris' backend_flag2 = 'ALLOW_TO_FAILOVER' 3) # - Authentication - enable_pool_hba = on pool_passwd = 'pool_passwd' num_init_children = 300 4) # - FILE LOCATIONS pid_file_name = '/opt/pgpool-4.2.0/pgpool/pgpool.pid' logdir = '/opt/pgpool-4.2.0/pgpool' 5) # - Master/Slave Mode master_slave_mode = on master_slave_sub_mode = 'stream' 6) # - HEALTH CHECK health_check_period = 300 health_check_timeout = 300 health_check_user = 'postgres' health_check_password = 'postgres' health_check_database = 'postgres' health_check_max_retries = 0 health_check_retry_delay = 1 connect_timeout = 10000 7) #FAILOVER AND FAILBACK failover_command = '/opt/pgpool-4.2.0/etc/failover.sh %d %h %D %m %H %R %M %P' fail_over_on_backend_error = on search_primary_node_timeout = 300 8) # ONLINE RECOVERY recovery_user = 'nobody' recovery_password = '' recovery_1st_stage_command = '' recovery_2nd_stage_command = '' recovery_timeout = 90 client_idle_limit_in_recovery = 0 09) # WATCHDOG use_watchdog = on trusted_servers = '' ping_path = '/bin' # - Watchdog communication Settings - hostname0 = '10.10.10.86' wd_port0 = 9000 pgpool_port0 = 9999 wd_priority = 1 wd_authkey = '' wd_ipc_socket_dir = '/tmp' hostname1 = '10.10.22.44' wd_port1 = 9000 pgpool_port1 = 9999 11) Lifecheck Setting - wd_monitoring_interfaces_list = 'any' wd_lifecheck_method = 'heartbeat' wd_interval = 10 -- heartbeat mode -- heartbeat_hostname0 = '10.10.18.86' heartbeat_port0 = 9694 heartbeat_device0 = '' heartbeat_hostname1 = '10.10.22.44' heartbeat_port1 = 9694 heartbeat_device1 = '' wd_heartbeat_keepalive = 2 wd_heartbeat_deadtime = 30 12) - Virtual IP control Setting - delegate_IP = '10.10.18.199' # delegate IP address if_cmd_path = '/usr/sbin' if_up_cmd = 'ip addr add $_IP_$/24 dev eth0 label eth0:0' if_down_cmd = 'ip addr del $_IP_$/24 dev eth0 label eth0:0' arping_path = '/usr/sbin' arping_cmd = 'arping -U $_IP_$ -w 1 -I eth0' 13 ) # - Behaivor on escalation Setting - clear_memqcache_on_escalation = on wd_escalation_command = '/opt/pgpool-4.2.0/etc/escalation.sh' wd_de_escalation_command = '/opt/pgpool-4.2.0/etc/de_escalation.sh' and edit the escalation and de_escalation script which is available in /opt/pgpool-4.2.0/etc/'
10 | create pgpool_node_id file | Shreeyansh team | If watchdog feature is enabled, to distingusish which host is which, a pgpool_node_id file is required. You need to create a 'pgpool_node_id' file and specify the pgpool (watchdog) node number (e.g. 0, 1, 2 ...) to identify pgpool (watchdog) host. create 'pgpool_node_id' file at '/opt/pgpool-4.2.0/etc' this location and in this file add your watchdog host id i.e.0,1,2 etc... cd /opt/pgpool-4.2.0/etc touch pgpool_node_id nano pgpool_node_id 0 -> only enter your hostid = i.e.0 or 1 sudo chown -R pgpool:pgpool /opt/pgpool-4.2.0/pgpool_node_id sudo chmod 755 /opt/pgpool-4.2.0/etc/pgpool_node_id
11 | Install 2 utilities | Shreeyansh team | sudo apt-get install net-tools sudo apt install arping
12 | ssh-keygen between pgpool to pgpool ,pgpool to postgres and pgpool(root) to postgres |  | ssh-keygen between prod117(pgpool) to postgres servers: ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65 ssh-keygen between prod117(pgpool root) to postgres servers: sudo -i ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65 ssh-keygen between prod119(pgpool) to postgres servers: ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65 ssh-keygen between prod119(pgpool root) to postgres servers: sudo -i ssh-keygen ssh-copy-id postgres@prod114 ssh-copy-id postgres@prod115 ssh-copy-id postgres@prod116 or using IP address ssh-copy-id postgres@10.10.22.63 ssh-copy-id postgres@10.10.22.64 ssh-copy-id postgres@10.10.22.65
13 | pool_hba.conf entries | Shreeyansh team | cd /opt/pgpool-4.2.0/etc nano pool_hba.conf host all all 10.10.18.81/24 md5 host all all 10.10.18.84/24 md5 host all all 10.10.18.85/24 md5 host all all 10.10.22.44/24 md5
14 | pgpool start script | Shreeyansh team | cd /opt/pgpool-4.2.0/etc nano pgpool_start.sh #!/bin/bash /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf -n -D > /opt/pgpool-4.2.0/pgpool/pgpool.log 2>&1 &
15 | pgpool stop script | Shreeyansh team | cd /opt/pgpool-4.2.0/etc nano pgpool_stop.sh #!/bin/bash /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf -n -D -mi stop > /opt/pgpool-4.2.0/pgpool/pgpool.log 2>&1 &
16 | systemctl start | Shreeyansh team | sudo systemctl start pgpool.service
17 | systemctl stop | Shreeyansh team | sudo systemctl stop pgpool.service
18 | systemctl status | Shreeyansh team | sudo systemctl status pgpool.service
19 | check the connectivity with postgres | Shreeyansh team | psql -p 9999 -U postgres -d postgres -h localhost
20 | Verfied connected nodes | Shreeyansh team | show pool_nodes;
Attach and detach nodes
1 | pcp attach node | Shreeyansh team | ./pcp_attach_node -p 9898 -U pgpool -v -n 0
2 | pcp_detach node | Shreeyansh team | ./pcp_detach_node -p 9898 -U pgpool -v -n 0
systemd pgpool service
1 | Steps to create a systemd pgpool service | Shreeyansh team | ssh pgpool@prod117 1. cd /etc/systemd/system 2. sudo nano pgpool.service 3. Add the below lines [Unit] Description=pgpool service After=network.target [Service] Type=forking User=root Group=root # Where to send early-startup messages from the server (before the logging # options of postgresql.conf take effect) # This is normally controlled by the global default set by systemd # StandardOutput=syslog # Disable OOM kill on the postmaster OOMScoreAdjust=-1000 # ... but allow it still to be effective for child processes # (note that these settings are ignored by Postgres releases before 9.5) Environment=PG_OOM_ADJUST_FILE=/proc/self/oom_score_adj Environment=PG_OOM_ADJUST_VALUE=0 # Maximum number of seconds pg_ctl will wait for postgres to start. Note that # PGSTARTTIMEOUT should be less than TimeoutSec value. #Environment=PGSTARTTIMEOUT=270 ExecStart=/opt/pgpool-4.2.0/etc/pgpool_start.sh ExecStop=/opt/pgpool-4.2.0/etc/pgpool_stop.sh ExecReload=/opt/pgpool-4.2.0/bin -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf reload # Give a reasonable amount of time for the server to start up/shut down. # Ideally, the timeout for starting PostgreSQL server should be handled more # nicely by pg_ctl in ExecStart, so keep its timeout smaller than this value. TimeoutSec=300 [Install] WantedBy=multi-user.target 4. sudo systemctl daemon-reload 5. sudo systemctl enable pgpool.service 6. sudo systemctl start pgpool.service
pgpool reload command
1 | Command Syntax | Shreeyansh team | pgpool [-c][-f config_file][-a hba_file][-F pcp_config_file] reload
2 | pgpool reload | Shreeyansh team | sudo /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf reload
3 | Scan1 pgpool reload command | Shreeyansh team | sudo /opt/pgpool-4.4/bin/pgpool -f /opt/pgpool-4.4/etc/pgpool.conf -F /opt/pgpool-4.4/etc/pcp.conf -a /opt/pgpool-4.4/etc/pool_hba.conf reload
4 | Scan2 pgpool reload command | Shreeyansh team | sudo /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf reload
5 | Dbtl pgpool reload command | Shreeyansh team | sudo /opt/pgpool-4.2.0/bin/pgpool -f /opt/pgpool-4.2.0/etc/pgpool.conf -F /opt/pgpool-4.2.0/etc/pcp.conf -a /opt/pgpool-4.2.0/etc/pool_hba.conf reload
Clear all pgpool log files except some files
1 | Clear pgpool logs except some files | Shreeyansh team | sudo rm -v !("failover.log"¦"pgpool-2021-08-06_000000.log"¦"pgpool.log"¦"pgpool.pid"¦"pgpool_status")

## Pgbadger&Pgcluu_Reports Links
Pgbadger Reports Links
Clusters | Host | Links
scan1 | prod60
scan1 | prod61 | http://10.10.18.187/pgbadger_reports/
scan1 | prod63
scan2 | prod114 | http://10.10.22.63/pgbadger_reports/prod114/
scan2 | prod115 | http://10.10.22.63/pgbadger_reports/prod115/
scan2 | prod116 | http://10.10.22.63/pgbadger_reports/prod116/
dbtl | prod107
dbtl | prod108
dbtl | prod109
dbtl.stage | stage85 | http://stage85/pgbadger_reports/
dbtl.stage | stage86 | http://stage86/pgbadger_reports/
dbtl.stage | stage87 | http://stage87/pgbadger_reports/
Pgcluu Reports Links
Clusters | Host | Links
scan1 | prod60
scan1 | prod61
scan1 | prod63
scan2 | prod114 | http://10.10.22.63/pgcluu_report_output/prod114/
scan2 | prod115 | http://10.10.22.63/pgcluu_report_output/prod115/
scan2 | prod116 | http://10.10.22.63/pgcluu_report_output/prod116/
dbtl | prod107
dbtl | prod108
dbtl | prod109
dbtl.stage | stage85
dbtl.stage | stage86 | http://10.10.19.76/pgcluu_report_output/stage86/
dbtl.stage | stage87